## PSSR Checklist
Conduct a mobile audit with Safesite.
iOS | Google Play | Desktop Browser
Language | English
Author | Safesite
Industry | General Industry
Description | A pre-startup safety review (PSSR) checklist is a tool used by a PSSR team during a safety review of a new or modified manufacturing facility before commissioning. This checklist helps ensure that a facility will be safe for employees and that equipment will operate according to design specifications.
Jurisdiction | USA Federal OSHA
Publish Date | 2020-03-01
Name | Pre-startup Safety Review Checklist - PSSR
Item Number | General Safety | Yes | No | N/A | Comments
1 | Have ALL appropriate personnel (Operations, Maintenance, Technical, and Supervision) received adequate and appropriate training on the equipment and operating procedures? | FALSE | FALSE | FALSE
2 | Has adequate and appropriate PPE (Personal Protective Equipment) been specified in the Work Procedures and/or Standard Operating Procedures. | FALSE | FALSE | FALSE
3 | Has the PPE been provided? | FALSE | FALSE | FALSE
4 | Have the PPE users been trained in the use of the PPE? | FALSE | FALSE | FALSE
5 | Is the training documented? | FALSE | FALSE | FALSE
6 | Have measures been taken to adequately guard all dangerous parts of this equipment? | FALSE | FALSE | FALSE
7 | Has sufficient provision been made for the electrical and/or mechanical isolation of the equipment? | FALSE | FALSE | FALSE
8 | Are points of isolation clearly marked/labeled and readily accessible? | FALSE | FALSE | FALSE
9 | Have bump/trip hazards been properly identified and adequately marked? | FALSE | FALSE | FALSE
10 | Have all sharp edges been removed? | FALSE | FALSE | FALSE
11 | Has proper guarding, handrails/barriers, been provided to prevent falls? | FALSE | FALSE | FALSE
12 | Have all hot/cold surfaces been adequately guarded to prevent burns? | FALSE | FALSE | FALSE
13 | Are all cold surfaces adequately insulated to prevent condensation drips (slip hazards)? | FALSE | FALSE | FALSE
14 | Are Safety Showers and Eye Wash facilities provided and adequately marked? | FALSE | FALSE | FALSE
15 | Are the Safety Showers and Eye Wash facilities routinely inspected? | FALSE | FALSE | FALSE
16 | Do the Safety Showers and Eye Wash facilities locations comply with Corporate guidelines? | FALSE | FALSE | FALSE
17 | Are the Safety Showers and Eye Wash facilities readily visible and accessible? | FALSE | FALSE | FALSE
18 | Has sufficient lighting been provided so that operation, servicing, maintenance and repair of the facilities can be carried out safely? | FALSE | FALSE | FALSE
19 | Are notices, dials, screens, etc. for providing operational instructions, safety warnings, and emergency information provided, if required, and positioned so that they are clearly visible and easily read? | FALSE | FALSE | FALSE
20 | Have all overhead fixtures, for example, pipe-hangers, pipe sleeves, pipe sleeve covers, valve handles, floor opening covers, etc., which could fall or be dislodged, been properly secured? | FALSE | FALSE | FALSE
21 | Are all of the applicable Work Permit Procedures (Conned Space Entry, Lock Out/Tag Out, Hot Work, High Work, etc.) in place? | FALSE | FALSE | FALSE
22 | Have the Operating, Maintenance, and Supervisory personnel been properly trained on the Work Permit Procedures? | FALSE | FALSE | FALSE
23 | Has the re protection systems been inspected by the insurance company? | FALSE | FALSE | FALSE
24 | Has acceptance testing been completed and documented? | FALSE | FALSE | FALSE
25 | Is there an agreed on test and inspection program for the re protection systems (including alarm systems)? | FALSE | FALSE | FALSE
| Machinery/Equipment Safety | Yes | No | N/A | Comments
26 | Has the machinery/equipment been installed so that it will be stable and secure during operation? | FALSE | FALSE | FALSE
27 | Has all access to dangerous moving parts, or danger zones created by the equipment, been prevented by the provision of the correct guards, interlocks (both safety & non-safety) and/or barriers? | FALSE | FALSE | FALSE
28 | Have the correct safety measures been taken to prevent any risk from hot/cold surfaces, ejection of material, failure of parts and their ejection, overheating/fire? | FALSE | FALSE | FALSE
29 | Has safe access been provided to the equipment that requires operator and calibration and maintenance personnel access for normal operations, adjustments, service, calibration, maintenance, or repair? | FALSE | FALSE | FALSE
30 | Have slip, trip, trap, crush, entanglement, fall, bump, and cut hazards been minimized? | FALSE | FALSE | FALSE
31 | Is the equipment provided with the properly identified START/STOP and EMERGENCY controls that are positioned for safe operation without hesitation, or loss of time, and without ambiguity? | FALSE | FALSE | FALSE
32 | Is the equipment provided with a clearly identified means to securely isolate it from ALL energy sources? | FALSE | FALSE | FALSE
| Ergonomics | Yes | No | N/A | Comments
33 | Have the workstations, workplace, or equipment been constructed so that need for stooping, bending stretching, over-reaching and working over-head during operation has been eliminated or minimized? | FALSE | FALSE | FALSE
34 | Has the need to lift, carry, push or pull heavy loads, or parts, been eliminated to the extent possible? | FALSE | FALSE | FALSE
35 | Are all display screens, dials and START/STOP/ EMERGENCY buttons positioned so that they are readily visible and accessible by the operating personnel? | FALSE | FALSE | FALSE
36 | Have Visual Display Screens been positioned so that interference from glare is reduced to the minimum? | FALSE | FALSE | FALSE
37 | Have workstations been designed and equipped so that the operator can adopt a comfortable position? (That is, able to stand, or change position and sit upright, angle at elbows and knees 90, feet on floor.) | FALSE | FALSE | FALSE
38 | Does the operation of this equipment increase the risk of Upper Limb Disorder; for example, repetitive tasks, handling operations, machine paced work and prolonged operation? | FALSE | FALSE | FALSE
| Occupational Health | Yes | No | N/A | Comments
39 | Have all health risks arising from the gases, liquids, dusts, mists, biological hazards or vapors used by, contained in or emitted by this equipment been assessed | FALSE | FALSE | FALSE
40 | Have the health risks been eliminated or are adequate engineering controls utilized to minimize the risks? | FALSE | FALSE | FALSE
41 | Has adequate RPE (Respiratory Protective Equipment) been specified in the Operating Procedures? | FALSE | FALSE | FALSE
42 | Has the need for an Occupational Health Monitoring Programme been assessed? | FALSE | FALSE | FALSE
43 | Has a Monitoring Programme been scheduled? | FALSE | FALSE | FALSE
44 | Have the Operating Procedures been reviewed to take into account any additional “health hazards” which may arise from operation or maintenance of this equipment? | FALSE | FALSE | FALSE
45 | Has adequate LEV (Local Exhaust Ventilation) been installed, tested, balanced, and entered on an Inspection Schedule? | FALSE | FALSE | FALSE
46 | Have adequate inspection/cleaning ports been provided on ductwork? | FALSE | FALSE | FALSE
47 | Are relief facilities directed to a safe place away from the workplace? | FALSE | FALSE | FALSE
48 | Has a Noise Survey been considered and a Noise Compliance Plan prepared, if required? | FALSE | FALSE | FALSE
49 | Has all insulation been identified? | FALSE | FALSE | FALSE
50 | Has all pipe work, tanks, and equipment containing hazardous materials been adequately labeled? | FALSE | FALSE | FALSE
| Process Safety | Yes | No | N/A | Comments
51 | Process Technology | FALSE | FALSE | FALSE
52 | Are up-to-date Material Safety Data Sheets available? | FALSE | FALSE | FALSE
53 | Have the hazardous effects of inadvertent mixing of different materials been considered (that is, has a chemical interaction matrix been prepared/updated)? | FALSE | FALSE | FALSE
54 | Has the process design basis been documented or updated? | FALSE | FALSE | FALSE
55 | Has the control philosophy and sequence of operations been documented? | FALSE | FALSE | FALSE
56 | Has the equipment design basis (for example, BPF’s/P&IDs) been documented/updated? | FALSE | FALSE | FALSE
57 | Have the recommendations from safety reviews, Process Hazards Analysis (PHA), Hazards and Operability Reviews (HAZOP), CHAZOP, or others, been implemented? | FALSE | FALSE | FALSE
58 | Record any incomplete items. | FALSE | FALSE | FALSE
59 | Are all relief devices shown on the P&IDs? | FALSE | FALSE | FALSE
60 | Are standard markings used on the relief devices? | FALSE | FALSE | FALSE
61 | Are the relief/rupture pressures included on the P&IDs? | FALSE | FALSE | FALSE
62 | Have the pressure relief device calculations been provided? | FALSE | FALSE | FALSE
63 | Was DIERS technology utilized to size the pressure relief devices for all pressure vessels? | FALSE | FALSE | FALSE
64 | Does the sizing of pressure relief devices agreed with the calculated sizes? | FALSE | FALSE | FALSE
65 | Do the calculations take into the downstream piping? | FALSE | FALSE | FALSE
66 | Do the relief devices vent to safe locations? | FALSE | FALSE | FALSE
67 | Is containment provided for liquids and solids released from pressure relief devices? | FALSE | FALSE | FALSE
68 | Are there isolation valves that, if closed, will inhibit the operation of pressure relief devices? | FALSE | FALSE | FALSE
69 | If yes, Operations must establish control plans to insure that the isolation valves cannot inhibit the operation of the pressure relief devices. | FALSE | FALSE | FALSE
70 | Are all pressure relief devices included in the Preventive Maintenance Program? | FALSE | FALSE | FALSE
71 | Are the inspection and testing of relief devices in accordance with local regulations? | FALSE | FALSE | FALSE
| Management of Change | Yes | No | N/A | Comments
72 | Has a management of change – technology/subtle change document (for example, Change of Design - COD) been approved? | FALSE | FALSE | FALSE
73 | Has a test authorization been approved? | FALSE | FALSE | FALSE
74 | Are all action items, arising from the COD, that were deemed necessary for startup, complete? | FALSE | FALSE | FALSE
75 | Have all changes made during construction been recorded and authorized? | FALSE | FALSE | FALSE
76 | Have hazards evaluations (PHAs, HAZOP, or CHAZOP) been done on all the changes made during construction? | FALSE | FALSE | FALSE
| Process Hazards Analysis | Yes | No | N/A | Comments
77 | Have project PHAs been approved and a final project safety report been prepared? | FALSE | FALSE | FALSE
78 | Are all action items, deemed necessary by the PHA team for start-up, complete? | FALSE | FALSE | FALSE
79 | Has the project been approved as “Safe to proceed with” by the PHA team? | FALSE | FALSE | FALSE
| Quality Assurance | Yes | No | N/A | Comments
80 | Have checks and inspections been made to ensure that critical equipment is installed properly and is consistent with design specifications and vendor’s recommendations (for example, alarm and interlock (safety & non-safety) tests; equipment alignment and service to process inter-connections)? | FALSE | FALSE | FALSE
81 | Have quality assurance inspection reports, covering fabrication, assembly, and installation, been completed in accordance with the project’s quality assurance plan and reports led with the equipment and design basis documentation? | FALSE | FALSE | FALSE
82 | List specific items field checked as part of this Pre-Start-up Safety Review to ensure that: | FALSE | FALSE | FALSE
83 | The construction meets the design specifications. | FALSE | FALSE | FALSE
84 | The construction matches the drawings. | FALSE | FALSE | FALSE
85 | Have the following documented been provided and approved: | FALSE | FALSE | FALSE
86 | Instrument indexes and instrument loop diagrams? | FALSE | FALSE | FALSE
87 | A tabulation, including settings, of interlocks (both safety & non-safety) and trips (hardwire and software), process alarms and permissive descriptions? | FALSE | FALSE | FALSE
88 | As-built drawings covering P&IDs, electrical, piping, and mechanical? | FALSE | FALSE | FALSE
89 | Data sheets for pressure equipment built to ASME or equivalent codes? | FALSE | FALSE | FALSE
90 | Welder certification? | FALSE | FALSE | FALSE
91 | Non-destructive test (NDT) certifications? | FALSE | FALSE | FALSE
92 | Electrical certification for classified areas? | FALSE | FALSE | FALSE
| Mechanical Integrity | Yes | No | N/A | Comments
93 | Have maintenance procedures been approved? | FALSE | FALSE | FALSE
94 | Have maintenance personnel been trained? | FALSE | FALSE | FALSE
95 | Have spare parts listed been developed and entered into the parts ordering software program? | FALSE | FALSE | FALSE
96 | Are there adequate inventories of spare parts, operating supplies and maintenance materials? | FALSE | FALSE | FALSE
97 | Have quality control procedures been approved for maintenance materials and spare parts? | FALSE | FALSE | FALSE
Have inspections and tests (including regulatory requirements) for the following equipment been included in a maintenance schedule?
98 | • Pressure vessels and storage tanks? | FALSE | FALSE | FALSE
99 | • Pressure relief systems, vent systems, and devices? | FALSE | FALSE | FALSE
100 | • Critical controls, interlocks (both safety & non-safety), alarms and instruments? | FALSE | FALSE | FALSE
101 | • Emergency devices (including shutdown systems and isolation systems)? | FALSE | FALSE | FALSE
102 | • Fire protection equipment? | FALSE | FALSE | FALSE
103 | • Piping systems (incl. Components, for example, valves, excess flow valves, expansion bellows) in critical service? | FALSE | FALSE | FALSE
104 | • Key process-to-service tie-ins? | FALSE | FALSE | FALSE
105 | • Electrical earthening, grounding, bonding? | FALSE | FALSE | FALSE
106 | • MCC starters? | FALSE | FALSE | FALSE
107 | • Emergency alarm and communication system? | FALSE | FALSE | FALSE
108 | • Monitoring devices and sensors? | FALSE | FALSE | FALSE
109 | • Pumps? | FALSE | FALSE | FALSE
110 | • Lifting equipment? | FALSE | FALSE | FALSE
111 | Has a reliability engineering analysis been considered/ completed for PSM critical equipment? | FALSE | FALSE | FALSE
112 | Is the equipment inspected by any outside body and certificates on le (for example, CE marking, lifting equipment test certificates, pressure systems regulations, and other items)? | FALSE | FALSE | FALSE
113 | Have all commissioning tests or inspections been identified (for example, pressure, or leak tests, passivating procedures)? | FALSE | FALSE | FALSE
| Operating Procedures & Safe Work Practices | Yes | No | N/A | Comments
114 | Have standard operating procedures been prepared/updated and approved? | FALSE | FALSE | FALSE
Do the operating procedures cover:
115 | • Initial start-up? | FALSE | FALSE | FALSE
116 | • Normal start-up? | FALSE | FALSE | FALSE
117 | • Normal operations? | FALSE | FALSE | FALSE
118 | • Normal shutdowns? | FALSE | FALSE | FALSE
119 | • Emergency operations including emergency shutdowns? | FALSE | FALSE | FALSE
120 | • Start-up after emergency shutdowns? | FALSE | FALSE | FALSE
121 | • Start-up following turnarounds/prolonged shutdowns? | FALSE | FALSE | FALSE
122 | • Non-routine procedure such as equipment clean-outs and preparation of equipment for maintenance? | FALSE | FALSE | FALSE
123 | • Auxiliary equipment operations including as examples; LEV and Ventilation Systems, Heat/Cool Skids, Water (Soft, RO, WFI, Tower, etc.) Systems, Instrument and Process Air Systems, Waste Treatment Systems, Cooling (Glycol Refrigeration) Systems, Steam Generation, and others? | FALSE | FALSE | FALSE
124 | • Safety and operational issues? | FALSE | FALSE | FALSE
125 | • Change control procedures? | FALSE | FALSE | FALSE
| Training and Performance | Yes | No | N/A | Comments
126 | Has specific process (or job task) training been given to personnel? | FALSE | FALSE | FALSE
127 | Have training records been updated? | FALSE | FALSE | FALSE
| Contractor Safety | Yes | No | N/A | Comments
128 | Have all contract personnel been adequately trained in appropriate: chemical awareness, maintenance, and operating activities and evacuation procedures? | FALSE | FALSE | FALSE
| Interlocks and Alarms | Yes | No | N/A | Comments
129 | Has the alarm/interlock (safety & non-safety) been classified and designed by the Project Team? Did the Project Team include members of the PHA team? | FALSE | FALSE | FALSE
130 | Did the loop testing confirm that the alarm/interlock (safety & non-safety) action proved, under all conceivable failure conditions, to be fail-safe? | FALSE | FALSE | FALSE
131 | Prior to this PSSR, has an interlock/critical alarm Standard Operating Procedure for testing, through to the final element, been prepared and reviewed/authorized by a competent person for each new or upgraded control system? | FALSE | FALSE | FALSE
132 | For alarms/interlocks (both safety & non-safety) with more than one software or hardware circuit, have all possible interlock routes been tested? | FALSE | FALSE | FALSE
133 | Has all appropriate process technology been updated (for example, interlock lists, P&IDs, logic drawings, etc.)? | FALSE | FALSE | FALSE
134 | Does your Control System documentation adequately specify: | FALSE | FALSE | FALSE
135 | All major components and their model and serial numbers? | FALSE | FALSE | FALSE
136 | All communication cables layout and configuration? | FALSE | FALSE | FALSE
137 | Any configurable or custom settings and set-up? | FALSE | FALSE | FALSE
138 | Has consideration been given to suitable re detection and prevention systems for the equipment? | FALSE | FALSE | FALSE
139 | Do you have an appropriate procedure to ensure that your software is protected (for example, routinely archived, key/password protected, etc.)? | FALSE | FALSE | FALSE
140 | Has the software been properly documented and led (for example, logic drawings, schematics, sequence/batch descriptions)? | FALSE | FALSE | FALSE
141 | Has all software been properly validated and tested? | FALSE | FALSE | FALSE
142 | Is there verification that the equipment does not re-start, either on the re-setting of a protective device such as an interlock (safety & non-safety), or the reestablishment of power after an outage? | FALSE | FALSE | FALSE
| Environmental | Yes | No | N/A | Comments
143 | Are all secondary containment/bonding facilities adequate? | FALSE | FALSE | FALSE
144 | Are all material storage facilities adequate and appropriately labeled? | FALSE | FALSE | FALSE
145 | Have adequate arrangements been made, prior to start-up, for the identification, classification, and safe disposal of all waste materials? | FALSE | FALSE | FALSE
146 | Have all materials, used in the system, been entered on the Area Chemicals Inventory List (or equivalent)? | FALSE | FALSE | FALSE
147 | Are updated Area Spill Procedures available? | FALSE | FALSE | FALSE
148 | Are material Unloading Facilities adequate and constructed in accordance with Corporate Safety, Health, and Environmental Standards? | FALSE | FALSE | FALSE
149 | Is there adequate containment (110% of truck volume) in the unloading areas for bulk liquid chemicals? | FALSE | FALSE | FALSE
150 | Have the Corporate Environmental Guidelines been followed during the design stage of this project? | FALSE | FALSE | FALSE
151 | Have all waste streams been identified, quantified, analyzed and minimized? | FALSE | FALSE | FALSE
152 | Are all of the applicable Construction, Environmental and Operating Permits up to-date and approved? | FALSE | FALSE | FALSE
| Community Awareness & Emergency Response | Yes | No | N/A | Comments
153 | Have all necessary precautions been taken to ensure that the equipment is not a source of ignition to any flammable materials, irrespective of their source? | FALSE | FALSE | FALSE
154 | Are re protection facilities adequate for example, re extinguishers, re walls, sprinkler systems, Alarm Boxes, etc.)? | FALSE | FALSE | FALSE
155 | Are Emergency Escape Routes, including ladders, adequate and properly signposted? | FALSE | FALSE | FALSE
156 | Is emergency lighting adequate? | FALSE | FALSE | FALSE
157 | Is sufficient Respiratory Protective Equipment, such as Escape Sets or Self-Contained Breathing Apparatus (SCBA) available? | FALSE | FALSE | FALSE
158 | Have Emergency Procedures been prepared and relevant personnel trained? | FALSE | FALSE | FALSE
159 | Is the Community Panel advised of proposed new major projects? | FALSE | FALSE | FALSE
160 | Has an Electrical Safety Checklist (Acceptance of Electrical Installations) been completed by a competent personnel? | FALSE | FALSE | FALSE
161 | Has the equipment been properly installed and constructed to Corporate guidelines and local legislation, and does it meet any special installation requirements noted on the manufacturer’s certificate? | FALSE | FALSE | FALSE
162 | Has equipment been designed and purchased for the conditions under which it will operate (for example, hazardous areas)? | FALSE | FALSE | FALSE
163 | Are all live parts adequately enclosed to prevent access? | FALSE | FALSE | FALSE
164 | Does grounding and bonding comply with corporate and local standards/legislation? | FALSE | FALSE | FALSE
165 | Have fuses or circuit breakers been provided which will automatically disconnect the supply? | FALSE | FALSE | FALSE
166 | Are First Aid Stations, single line drawings and PPE requirements available in Motor Control Centers (MCC), Electrical Control Rooms (ECR)/Sub-stations, as appropriate? | FALSE | FALSE | FALSE
167 | Have all relevant documentation and drawings (for example, P&IDs, SLDs, Schematics, equipment arrangement, I/O, logic, electrical classification and Panel Schedule drawings) been updated to reflect the current installation? | FALSE | FALSE | FALSE
168 | Have all new Sub-station Breakers, MCC isolators, starters or other appropriate equipment been registered on to the Site Inspection Schedule? | FALSE | FALSE | FALSE
169 | Have any electrical circuits, made redundant by this installation, been properly D&R’d? | FALSE | FALSE | FALSE
| Field verification | Yes | No | N/A | Comments
170 | Is the normal lighting adequate for normal and maintenance operations? | FALSE | FALSE | FALSE
171 | Is emergency lighting sufficient? | FALSE | FALSE | FALSE
172 | Are all hot and cold surfaces, which may cause burns, in the proximity of personnel insulated? | FALSE | FALSE | FALSE
173 | Are all instruments, equipment and piping adequately labeled? | FALSE | FALSE | FALSE
174 | Is there any rusted and/or damaged equipment? | FALSE | FALSE | FALSE
175 | Are swing gates or chains installed at the top of ladders and/or on access platforms? | FALSE | FALSE | FALSE
176 | Are there any gaps between platforms and equipment that could create a foot hazard? | FALSE | FALSE | FALSE
177 | Is equipment and platform access adequate? | FALSE | FALSE | FALSE
178 | Do safety showers/eye wash stations create a hazard to personnel (slips), potential for contamination of product (entry to equipment) or ingress to electrical equipment? | FALSE | FALSE | FALSE
179 | Are safety showers and eye wash stations adequately marked and readily visible? | FALSE | FALSE | FALSE
180 | Is the access to the safety showers and eye wash stations uninhibited? | FALSE | FALSE | FALSE
181 | Are all pipelines labeled? | FALSE | FALSE | FALSE
182 | Are all electrical switches, disconnects, MCCs, control panels, cables, etc labeled? | FALSE | FALSE | FALSE
183 | Is all the equipment clearly labeled? | FALSE | FALSE | FALSE
184 | Where required are the materials and hazards included on the labeling? | FALSE | FALSE | FALSE
185 | Are wall penetrations adequately sealed? | FALSE | FALSE | FALSE
186 | Are electrical conduits sealed in accordance with code requirements? | FALSE | FALSE | FALSE
187 | Are evacuation routes clearly marked? | FALSE | FALSE | FALSE
188 | Are re extinguishers installed properly? | FALSE | FALSE | FALSE
189 | Has the required signage been posted? | FALSE | FALSE | FALSE
190 | Are emergency stops provided where there is a potential for entrapment or exposure? | FALSE | FALSE | FALSE
191 | Has all scaffolding and construction equipment been removed? | FALSE | FALSE | FALSE
192 | Is housekeeping acceptable? | FALSE | FALSE | FALSE
193 | Is all required equipment guarding installed | FALSE | FALSE | FALSE
194 | Does all the applicable equipment have the required CE marking displayed? | FALSE | FALSE | FALSE
195 | Does all the applicable equipment have the required UL listing/labeling? | FALSE | FALSE | FALSE
196 | Have noise-monitoring evaluations been completed? | FALSE | FALSE | FALSE
197 | Have signs been posted where noise levels excess 85dB? | FALSE | FALSE | FALSE
198 | Are ear-plugs available near areas exceeding 85 dB? | FALSE | FALSE | FALSE
| Completion | Yes | No | N/A | Comments
199 | Safe and ready for commissioning/startup? | FALSE | FALSE | FALSE
Text | Write Comments or Remarks here: